## Slide 1
Project Status Report #2
RustCommerce | 2026-02-24 23:01
Amenthyx AI Teams — Virtual Engineering

## Slide 2
Executive Summary
Overall Status: ON TRACK
Completion: 88% (23/26 tasks done)
In Progress: 1 | In Review: 1 | Backlog: 1

## Slide 3
Milestone Progress
# Milestones — RustCommerce Plugin **Document Version**: 1.0 **Date**: 2026-02-24 **Status**: Active --- ## Overview | Milestone | Name | Status | Dependencies | |-----------|------|--------|--------------| | **M1** | Backend Foundation | Planned | Wave 0 (Initialization) | | **M2** | Cart & Checkout | Planned | M1 | | **M3** | Admin Dashboard | Planned | M1, M2 (partial) | | **M4** | Storefront & Polish | Planned | M1, M2, M3 | | **M5** | Testing & Release | Planned | M1, M2, M3, M4 | --- ## M1: Backend Foundation **Objective**: Establish the core backend infrastructure — database schema, product CRUD, category system, plugin integration, and REST API scaffolding. ### Deliverables | # | Deliverable | Owner | Status | |---|------------|-------|--------| | M1.1 | Database schema design and 7 migration files | Backend | Planned | | M1.2 | Product models (Product, ProductVariant) | Backend | Planned | | M1.3 | Product repository (CRUD operations via sqlx) | Backend | Planned | | M1.4 | Product service (business logic layer) | Backend | Planned | | M1.5 | Product API handlers (Axum route handlers) | Backend | Planned | | M1.6 | Category/Tag models and repository | Backend | Planned | | M1.7 | Category system integration with RustPress taxonomy | Backend | Planned | | M1.8 | Plugin trait implementation (`RustCommercePlugin`) | Backend | Planned | | M1.9 | Hook registration for key events | Backend | Planned | | M1.10 | Route definitions (`routes.rs`) | Backend | Planned |

## Slide 4
Kanban Snapshot
Backlog: 1
In Progress: 1
In Review: 1
Done: 23
# Kanban Board — RustCommerce Plugin **Last Updated**: 2026-02-24 **Legend**: - `[ ]` = Backlog - `[~]` = In Progress - `[?]` = In Review - `[x]` = Done --- ## Wave 0: Initialization - [x] Create project repository structure - [x] Set up `.ai/context/` with STRATEGY.md and CONTEXT_BASE.md - [x] Define initial `plugin.json` configuration - [x] Create skeleton Rust code (Product, Cart, Order structs) - [x] Set up Cargo.toml with dependencies --- ## Wave 1: Planning - [x] PROJECT_CHARTER.md — Project charter and scope definition - [x] MILESTONES.md — Milestone definitions and acceptance criteria - [x] KANBAN.md — This board - [x] TIMELINE.md — Wave-based execution timeline - [x] RISK_REGISTER.md — Risk register (R1-R10) - [x] GitHub Issues — Create labels, milestones, and issue backlog - [x] Sprint 1 planning — Assign first batch of M1 tasks --- ## Wave 1.5: Marketing + Legal (Background) ### Marketing - [x] Define product positioning and messaging - [x] Create landing page content for RustCommerce - [x] Prepare launch announcement blog post - [x] Create demo screenshots / video storyboard - [x] Plugin marketplace listing draft ### Legal - [x] License selection and LICENSE file (MIT / Apache 2.0) - [x] Terms of Service for store owners - [x] Privacy policy template for stores - [x] Stripe compliance review (PCI-DSS awareness) - [x] Open-source contribution guidelines (CONTRIBUTING.md) --- ## Wave 2: Engineering ### M1: Backend Foundation #### Database & Models - [x] Design database schema (ERD for all 7 migration files) - [x] Migration 00001: ecommerce_core (products, categories, variants) - [x] Migration 00002: cart_and_orders (cart, orders, order items) - [x] Migration 00003: customers (customers, addresses) - [x] Migration 00004: payments (payments, transactions) - [x] Migration 00005: shipping_and_tax (shipping zones/methods, tax zones/rates) - [x] Migration 00006: coupons (coupons, discount rules) - [x] Migration 00007: reviews (product reviews) -

## Slide 5
Blockers & Risks
# Risk Register — RustCommerce Plugin **Document Version**: 1.0 **Date**: 2026-02-24 **Status**: Active **Review Frequency**: Each wave boundary --- ## Risk Matrix Legend **Probability**: H (High) / M (Medium) / L (Low) **Impact**: H (High) / M (Medium) / L (Low) **Severity** = Probability x Impact: Critical / Major / Moderate / Minor | | Impact: High | Impact: Medium | Impact: Low | |---|---|---|---| | **Prob: High** | Critical | Major | Moderate | | **Prob: Medium** | Major | Moderate | Minor | | **Prob: Low** | Moderate | Minor | Minor | --- ## Active Risks ### R1: Stripe API Integration Complexity | Field | Detail | |-------|--------| | **ID** | R1 | | **Category** | Technical | | **Description** | Stripe API integration (PaymentIntents, webhooks, refunds) is complex and has strict security requirements. The `stripe-rust` crate may lack features, have breaking changes, or insufficient documentation for production use cases. Webhook signature verification and idempotency handling add further complexity. | | **Probability** | **M** (Medium) | | **Impact** | **H** (High) — Payment is the most critical feature; failure blocks checkout | | **Severity** | **Major** | | **Mitigation** | 1. Evaluate `stripe-rust` crate maturity early in M2; if insufficient, plan for raw HTTP client with Stripe REST API. 2. Build a payment gateway abstraction layer so Stripe implementation can be swapped. 3. Use Stripe test mode extensively. 4. Implement comprehensive webhook retry logic.

## Slide 6
Team Activity
# Team Status — RustCommerce Plugin **Last Updated**: 2026-02-24 **Reporting Period**: Wave 2 Engineering Complete --- ## Team Member Status | Role | Agent | Status | Deliverables | |------|-------|--------|--------------| | **PM** | Project Manager | Active | Reporting, tracking, coordination | | **BE** | Backend Engineer | Completed | 5 artifacts delivered | | **FE** | Frontend Engineer | Completed | 5 artifacts delivered | | **DevOps** | DevOps Engineer | Completed | 5 artifacts delivered | | **Infra** | Infrastructure Engineer | Completed | 5 artifacts delivered | | **Marketing** | Marketing Specialist | Completed | 5 artifacts delivered | | **Legal** | Legal Counsel | Completed | 5 artifacts delivered | | **QA** | QA Engineer | In Progress | Wave 3 testing underway | | **RM** | Release Manager | Standby | Awaiting Wave 3 completion | --- ## Artifacts Produced ### PM Artifacts (Planning — Wave 1) | File | Path | Size | |------|------|------| | PROJECT_CHARTER.md | `.team/PROJECT_CHARTER.md` | 10,213 bytes | | MILESTONES.md | `.team/MILESTONES.md` | 13,236 bytes | | KANBAN.md | `.team/KANBAN.md` | 9,643 bytes | | TIMELINE.md | `.team/TIMELINE.md` | 10,661 bytes | | RISK_REGISTER.md | `.team/RISK_REGISTER.md` | 13,280 bytes | | GITHUB_ISSUES.md | `.team/GITHUB_ISSUES.md` | 9,012 bytes | ### Backend Engineer Artifacts (API Contracts — Wave 2) | File | Path | Size | |------|------|------| | API_DESIGN.md | `.team/api-contracts/API_DESIGN.md` | 91,809 bytes | | AUTH_FL

## Slide 7
Next Steps
Planned for next reporting period: - Continue wave-based execution - Monitor quality gates - Update risk register - Coordinate cross-team dependencies - Generate next status report at T+6h